## Sheet1
Activity Chart |  |  |  | Gnatt Chart 1 - Ascending by Team Member
Task: | Duration: (hours) | Predecessor: | Actual: (hours) | Week 1 | Week 2 |  | Week 3 |  | Week 4 | Week 5 |  | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 |  | Week 12 | Week 13 | Week 14 | Week 15
1. CH Collect Requirements | 45 |  | 52
2. CH Prototype Design | 9 | 1 | 12 | [8 empty] | 1
3. CH Add Map | 9 | 2 | [10 empty] | 2
4. CH Add Enemies | 9 | 3 | [11 empty] | 3
5. CH Wave Algorithm | 27 | 4 | [12 empty] | 4
6. CH Add Assets | 9 | 2 | [10 empty] | 2
7. CH Testing | 27 | 4,5 | [16 empty] | 4,5
1. DS Collect Requirements | 60 |  | 60
2. DS Prototype Design | 12 | 1 | 24 | [8 empty] | 1
3. DS Enemy Movement | 36 | 2 | 36 | [9 empty] | 2
4. DS Damage to Player | 24 | 3 | [13 empty] | 3
5. DS Damage from Bullets | 36 | 3 | [13 empty] | 3
6. DS Damage from Traps | 12 | 4,5 | [17 empty] | 4,5
7. DS Testing | 24 | 6 | [18 empty] | 6
1. JA Software Analysis | 12 |  | 3
2. JA Create Start Menu | 4 | 1 | 1 | [5 empty] | 1
3. JA Create Pause Menu | 4 | 2 | [7 empty] | 2
4. JA Add Sound Architecture | 6 | 1 | [6 empty] | 1
5. JA Add Sound | 3 | 4 | [8 empty] | 4
1. SH Software Analysis | 6 |  | 8
2. SH Create Player Object | 2 | 1 | 2 |  |  | 1
3. SH Create Camera | 2 | 2 | 3 |  |  |  | 2
4. SH Collect Input | 2 | 3 | 2 |  |  |  |  | 3
5. SH Add Movement | 3 | 4 | 3 | [5 empty] | 4
6. SH Add Rotation | 4 | 4 | 4 | [5 empty] | 4
7. SH Add Weapons | 1 | 4 | [6 empty] | 4
8. SH Add Movement Bounds | 4 | 5,6,7 | [7 empty] | 5,6,7
9. SH Add Health/Death | 1 | 3 | [5 empty] | 3
Activity Chart |  |  |  | Gnaat Chart 2 - Ascending by Task Number
Task: | Duration: (hours) | Predecessor: | Actual: (hours) | Week 1 | Week 2 |  | Week 3 |  | Week 4 | Week 5 |  | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 |  | Week 12 | Week 13 | Week 14 | Week 15
1. CH Collect Requirements | 45 |  | 52
1. DS Collect Requirements | 60 |  | 60
1. JA Software Analysis | 12 |  | 3
1. SH Software Analysis | 6 |  | 8
2. CH Prototype Design | 9 | 1 | 12 | [8 empty] | 1
2. DS Prototype Design | 12 | 1 | 24 | [8 empty] | 1
2. JA Create Start Menu | 4 | 1 | 1 | [5 empty] | 1
2. SH Create Player Object | 2 | 1 | 2 |  |  | 1
3. CH Add Map | 9 | 2 | [10 empty] | 2
3. DS Enemy Movement | 36 | 2 | 36 | [9 empty] | 2
3. JA Create Pause Menu | 4 | 2 | [7 empty] | 2
3. SH Create Camera | 2 | 2 | 3 |  |  |  | 2
4. CH Add Enemies | 9 | 3 | [11 empty] | 3
4. DS Damage to Player | 24 | 3 | [13 empty] | 3
4. JA Add Sound Architecture | 6 | 1 | [6 empty] | 1
4. SH Collect Input | 2 | 3 | 2 |  |  |  |  | 3
5. CH Wave Algorithm | 27 | 4 | [12 empty] | 4
5. DS Damage from Bullets | 36 | 3 | [13 empty] | 3
5. JA Add Sound | 3 | 4 | [8 empty] | 4
5. SH Add Movement | 3 | 4 | 3 | [5 empty] | 4
6. CH Add Assets | 9 | 2 | [10 empty] | 2
6. DS Damage from Traps | 12 | 4,5 | [17 empty] | 4,5
6. SH Add Rotation | 4 | 4 | 4 | [5 empty] | 4
7. CH Testing | 27 | 4,5 | [16 empty] | 4,5
7. DS Testing | 24 | 6 | [18 empty] | 6
7. SH Add Weapons | 1 | 4 | [6 empty] | 4
8. SH Add Movement Bounds | 4 | 5,6,7 | 4 | [6 empty] | 5,6,7
9. SH Add Health/Death | 1 | 3 | [5 empty] | 3
Estimations:
CH estimated approx. 9 hours. per week
DS estimated approx. 12 hours per week
JA estimated approx. 4 hours per week
SH estimated approx. 4 hours per week
0